## Sheet1
Steps | Modules | Sub-Tasks
Note: Use the sections which you feel are valid for your project.
Business & Data Understanding
| Define the Scope of the ML Application | Business Problem | Staff is manually counting the number of 8mm, 16mm, 32mm, etc., steel rods in inventory. This is both time consuming and error prone.
|  | Business Objectives (maximum 4 to 5 words & to the extent possible please use terms such as Minimize & Maximize) | Minimize the time taken in counting the steel rods
Success Criteria
Business Success Criteria : Reduce the time taken in counting the steel rods by at least 75%
|  | Economic Success Criteria | By reducing the manual effort, we shall save at least 10LPA.
Feasibility
|  | Applicability of ML technology | Segmentation Algorithm
|  | Legal constraints | Minimize manual effort
|  | Requirements on the application | To solve the deficiencies of traditional manual bar counting
| Data Collection |  | Client Data Given
|  | Data version control | The Version 2.0 is used in this project
Data Quality Verification
Data description
Data requirements
Data verification
Data Preparation
Select Data
Feature selection
Data selection
Unbalanced Classes
Clean Data
Noise reduction
Data imputation
Construct Data
Feature engineering
Data augmentation
Standardize Data
File format
Normalization
Modeling
Literature research on similar problems
Define quality measures of the model
Performance
Robustness
Scalability
Explainability
Model Complexity
Resource Demand
Model Selection
Incorporate domain knowledge
Model training
Using unlabeled data and pre-trained models
Model Compression
Ensemble methods
Assure reproducibility
Method reproducibility
Result reproducibility
Experimental Documentation
Evaluation
Validate performance
Determine robustness
Increase explainability for ML practitioner & end user
Compare results with defined success criteria
Deployment
| Define inference hardware |  | Windows OS, 4GB RAM
| Model evaluation under production condition |  | NA
| Assure user acceptance and usability |  | NA
| Minimize the risks of unforeseen errors |  | NA
| Deployment strategy |  | Streamlit API
Monitoring and Maintenance
| Non-stationary data distribution |  | NA
| Degradation of hardware |  | NA
| System updates |  | NA
| Monitor |  | NA
| Update |  | NA
Note on C9: ====== ID#AAAAxC1i8qs Sharat (2023-05-16 06:20:29) Define the purpose and the success criteria of the ML application from a business point of view. eg: "sales increased by 13%".
Note on C10: ====== ID#AAAAxC1i8o4 Sharat (2023-05-16 06:20:29) Define the business objective into ML success criteria eg: "accuracy greater 95%"
Note on C11: ====== ID#AAAAxC1i8qI Sharat (2023-05-16 06:20:29) Add an economic success criterion to the project. eg: "cost savings with automated quality check per each product".
Note on C14: ====== ID#AAAAxC1i8qc Sharat (2023-05-16 06:20:29) Legal issues are essential for any business application. Verify for Legal constraints and record them.
Note on C15: ====== ID#AAAAxC1i8p8 Sharat (2023-05-16 06:20:29) The requirements include robustness, scalability, explainability and resource demand and are used for the development and verification
Note on C17: ====== ID#AAAAxC1i8rE Sharat (2023-05-16 06:20:29) Modification on the data set should be documented.
Note on C19: ====== ID#AAAAxC1i8o8 Sharat (2023-05-16 06:20:29) The data should be described by their statistical properties. Information about format, units, etc, of each input is required (domain knowledge)
Note on C20: ====== ID#AAAAxC1i8rQ Sharat (2023-05-16 06:20:29) The requirements can be the expected feature values (a range for continuous features or a list for discrete features) and the format of the data. Requirements have to be defined carefully to include all possible real world values.
Note on C21: ====== ID#AAAAxC1i8rY Sharat (2023-05-16 06:20:29) The initial data, and added data has to be checked according to the requirements. The best practice to use data exploration techniques to investigate the sample distribution.
Note on C24: ====== ID#AAAAxC1i8pU Sharat (2023-05-16 06:20:29) Select a good data feature representation based on the available measurements. Features should be analyzed by a domain expert. Feature selection methods can be separated into three categories: 1) filter methods: select features from data without considering the model 2) wrapper methods: use a learning model to evaluate the significance of the features 3) embedded methods: combination of above both methods
Note on C25: ====== ID#AAAAxC1i8sA Sharat (2023-05-16 06:20:29) Discard the samples strictly based on objective quality criteria. Should be well documented and
Note on C26: ====== ID#AAAAxC1i8qA Sharat (2023-05-16 06:20:29) Verify for Imbalance in the Data. Trying out different sampling techniques could improve the results. Comparing the results of different sampling techniques’ reduces the risk of introducing bias to the model.
Note on C28: ====== ID#AAAAxC1i8qg Sharat (2023-05-16 06:20:29) Noise/irrelevant features should be filtered to improve the signal-to-noise ratio. Filtered data to be documented and evaluated. Filter could remove important parts of the data.
Note on C29: ====== ID#AAAAxC1i8qk Sharat (2023-05-16 06:20:29) Missing, NAN and special values could be imputed with a model readable value. To reduce the risk of introducing substitution artifacts, the performance of the model should be compared between different imputation techniques.
Note on C31: ====== ID#AAAAxC1i8pM Sharat (2023-05-16 06:20:29) New features could be derived from existing ones based on domain knowledge.
Note on C32: ====== ID#AAAAxC1i8pA Sharat (2023-05-16 06:20:29) : Data augmentation utilizes known invariances in the data to perform a label preserving transformation to construct new data.
Note on C34: ====== ID#AAAAxC1i8rg Sharat (2023-05-16 06:20:29) The comma separated values (CSV) format is the most generic standard
Note on C35: ====== ID#AAAAxC1i8qE Sharat (2023-05-16 06:20:29) Features could be defined on different scales and might lead to strong bias to features on larger scales, hence normalization is required.
Note on A36: ====== ID#AAAAxC1i8pw Sharat (2023-05-16 06:20:29) The goal of the modeling phase is to craft one or multiple models that satisfy the given constraints and requirements. The choice of modeling techniques depends on the ML and the business objectives, the data and the boundary conditions of the project.
Note on C37: ====== ID#AAAAxC1i8o0 Sharat (2023-05-16 06:20:29) Sharat: Research the publications, patents, internal reports, etc for existing solutions on the business problem that we are working on.
Note on C38: ====== ID#AAAAxC1i8pc Sharat (2023-05-16 06:20:29) Evaluate the models on at least six complementary properties
Note on C39: ====== ID#AAAAxC1i8pQ Sharat (2023-05-16 06:20:29) Accuracy / performance on unseen data
Note on C40: ====== ID#AAAAxC1i8p0 Sharat (2023-05-16 06:20:29) Resiliency to inconsistent inputs and to failures in the execution environment
Note on C41: ====== ID#AAAAxC1i8r8 Sharat (2023-05-16 06:20:29) Ability to scale to high data volume in the production system
Note on C42: ====== ID#AAAAxC1i8rU Sharat (2023-05-16 06:20:29) Direct or post-hoc explainability
Note on C43: ====== ID#AAAAxC1i8ps Sharat (2023-05-16 06:20:29) Capacity should suit the data complexity
Note on C44: ====== ID#AAAAxC1i8qM Sharat (2023-05-16 06:20:29) Resource consumption/demand for deployment
Note on C45: ====== ID#AAAAxC1i8pg Sharat (2023-05-16 06:20:29) The model selection depends on the data and has to be tailored to the problem.
Note on C46: ====== ID#AAAAxC1i8rs Sharat (2023-05-16 06:20:29) Adding domain knowledge should always increase the quality of the model. It is best practice to validate the incorporated domain knowledge with respect to a general model.
Note on C47: ====== ID#AAAAxC1i8qY Sharat (2023-05-16 06:20:29) The trained model depends on the learning problem and as such are tightly coupled. The learning problem contains an objective, optimizer, regularization and cross-validation.
Note on C48: ====== ID#AAAAxC1i8po Sharat (2023-05-16 06:20:29) Labeling data could be very expensive and might limit the available data set size. Perform techniques like unsupervised pre-training and semi-supervised learning to handle unlabeled data.
Note on C49: ====== ID#AAAAxC1i8pE Sharat (2023-05-16 06:20:29) Compression or pruning methods could be used to obtain a more compact model.
Note on C50: ====== ID#AAAAxC1i8qo Sharat (2023-05-16 06:20:29) Sharat:
Note on C51: ====== ID#AAAAxC1i8q4 Sharat (2023-05-16 06:20:29) ML models are difficult to reproduce. To accept the models to generalised conditions reproducibility is a primary characteristic.
Note on C52: ====== ID#AAAAxC1i8ro Sharat (2023-05-16 06:20:29) Reproducing the model from an extensive description or sharing of the used algorithm, data set, hyper-parameters and prdouction environment.
Note on C53: ====== ID#AAAAxC1i8qw Sharat (2023-05-16 06:20:29) Large performance variances indicate the sensitivity of the algorithm and question the robustness of the model.
Note on C54: ====== ID#AAAAxC1i8pY Sharat (2023-05-16 06:20:29) Keeping track of the changed model’s performance and its causes allows model comprehension by addressing which modifications were beneficial and improve the overall model quality.
Note on C56: ====== ID#AAAAxC1i8q0 Sharat (2023-05-16 06:20:29) A major risk is that the test set cannot cover all possible inputs due to the large input dimensionality or exceptional cases. It is recommended to separate the teams and the procedures collecting the training and the test data to erase dependencies and avoid methodology dependence.
Note on C57: ====== ID#AAAAxC1i8qQ Sharat (2023-05-16 06:20:29) A major risk occurs if ML applications are not robust to noisy or wrong, or even designed adversarial input data Verification approaches and robustness validation methods using cross-validation techniques on historical data exist.
Note on C58: ====== ID#AAAAxC1i8rI Sharat (2023-05-16 06:20:29) Explainability of a model helps to find errors and allows strategies, e.g. by enriching the data set, to improve the overall performance.
Note on C59: ====== ID#AAAAxC1i8rc Sharat (2023-05-16 06:20:29) Domain and ML experts have to decide if the model can be deployed. The best practice is to document the results of the evaluation phase and compare them to the business and ML success criteria defined.
Note on C61: ====== ID#AAAAxC1i8rk Sharat (2023-05-16 06:20:29) Selecting the right hardware based on the requirements defined in the initial stages or align with an existing hardware. Cloud services offer scalable computation resources, but they have hard constraints.
Note on C62: ====== ID#AAAAxC1i8q8 Sharat (2023-05-16 06:20:29) The best practice to evaluate the performance of the model under incrementally increasing production conditions by iteratively running the tasks.
Note on C63: ====== ID#AAAAxC1i8pI Sharat (2023-05-16 06:20:29) The best practice to build a prototype and run an field test with end users. Examine the acceptance, usage rate and the user experience.
Note on C64: ====== ID#AAAAxC1i8rA Sharat (2023-05-16 06:20:29) Unforeseen errors and outage times could cause system shutdowns and a temporary suspension of services. A fall-back plan, that is activated in case of e.g. erroneous model updates or detected bugs is helpful.
Note on C65: ====== ID#AAAAxC1i8rM Sharat (2023-05-16 06:20:29) Before rolling out a model, it is best practice to setup an e.g. incremental deployment strategy that includes a pipeline for models and data.
Note on C66: ====== ID#AAAAxC1i8sE Sharat (2023-05-16 06:20:29) ML models are used over a long period and have a life cycle which has to be managed. The risk of not maintaining the model is the degradation of the performance over time which leads to false predictions and could cause errors in subsequent systems.
Note on C67: ====== ID#AAAAxC1i8p4 Sharat (2023-05-16 06:20:29) A shift in the features and/or in the labels are possible. This degrades the performance of the model over time.
Note on C68: ====== ID#AAAAxC1i8pk Sharat (2023-05-16 06:20:29) The hardware that the model is deployed on and the sensor hardware will age over time.
Note on C69: ====== ID#AAAAxC1i8rw Sharat (2023-05-16 06:20:29) Updates on the software or hardware of the system can cause a shift in the environment.
Note on C70: ====== ID#AAAAxC1i8r4 Sharat (2023-05-16 06:20:29) Monitor all input signals and notify when an update has occurred. The statistics of the incoming data and the predicted labels can be compared to the statistics of the training data. This phase also includes a comparison of the performance with the defined success criteria.
Note on C71: ====== ID#AAAAxC1i8qU Sharat (2023-05-16 06:20:29) Instead of training a completely new model from scratch, it is advised to fine-tune the existing model to new data. The performance of the updated model should be compared against the previous versions and could give insights on the time scale of model degradation. The automation of the update strategy can be boosted up to a continuous training and continuous deployment of the ML application while covering the defined quality assurance methods.